## Sheet1
[5 empty] | 46237 | 46238 | 46239 | 46240 | 46241 | 46244 | 46245 | 46246 | 46247 | 46248 | 46251 | 46252 | 46253 | 46254 | 46255 | 46258 | 46259 | 46260 | 46261 | 46262 | 46265 | 46266 | 46267 | 46268 | 46269 | 46272 | 46273 | 46274 | 46275 | 46276 | 46279 | 46280 | 46281 | 46282 | 46283 | 46286 | 46287 | 46288 | 46289 | 46290 | 46293 | 46294 | 46295 | 46296 | 46297 | 46300 | 46301 | 46302 | 46303 | 46304 | 46307 | 46308 | 46309 | 46310 | 46311 | 46314 | 46315 | 46316 | 46317 | 46318 | 46321 | 46322 | 46323 | 46324 | 46325 | 46328 | 46329 | 46330 | 46331 | 46332 | 46335 | 46336 | 46337 | 46338 | 46339
WBS | Task Name | Duration | Start date | Finish Date | 46237: w1; 46244: w2; 46251: w3; 46258: w4; 46265: w5; 46272: w6; 46279: w7; 46286: w8; 46293: w9; 46300: w10; 46307: w11; 46314: w12; 46321: w13; 46328: w14; 46335: w15
[5 empty] | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6 | T2 | T3 | T4 | T5 | T6
| PROJECT OVERVIEW | 6 | 2026-08-03 | 2026-08-10 | bar: w1 T2 to w2 T2
0.1 | Project Introduction | 2 | 2026-08-03 | 2026-08-04 | bar: w1 T2 to w1 T3
0.2 | Business objective | 1 | 2026-08-05 | 2026-08-05 | bar: w1 T4
0.3 | SWOT Analysis | 2 | 2026-08-06 | 2026-08-07 | bar: w1 T5 to w1 T6
0.4 | Expected Benefits | 1 | 2026-08-10 | 2026-08-10 | bar: w2 T2
0.5 | Budget estimate and financial analysis | 3 | 2026-08-06 | 2026-08-10 | bar: w1 T5 to w2 T2
1 | INITIATING | 4 | 2026-08-11 | 2026-08-14 | bar: w2 T3 to w2 T6
1.1 | Stakeholder identification | 1 | 2026-08-11 | 2026-08-11 | bar: w2 T3
1.2 | Project Charter | 2 | 2026-08-12 | 2026-08-13 | bar: w2 T4 to w2 T5
1.3 | Kick-off Meeting | 1 | 2026-08-14 | 2026-08-14 | bar: w2 T6
2 | PLANNING | 5 | 2026-08-17 | 2026-08-21 | bar: w3 T2 to w3 T6
3 | EXECUTING | 2 | 2026-08-03 | 2026-08-04 | bar: w1 T2 to w1 T3
3.1 | Requirements Gathering | 1 | 2026-08-03 | 2026-08-03 | bar: w1 T2
3.2 | User Inputs Documentation | 1 | 2026-08-03 | 2026-08-03 | bar: w1 T2
3.3 | Course Portal Content Development | 2 | 2026-08-03 | 2026-08-04 | bar: w1 T2 to w1 T3
3.4 | Course Portal Design (UI/UX) | 1 | 2026-08-03 | 2026-08-03 | bar: w1 T2
3.5 | Course Portal Construction (Development & Database Setup) | 1 | 2026-08-03 | 2026-08-03 | bar: w1 T2
3.6 | Course Portal Testing (Functional, Performance, Security) | 1 | 2026-08-03 | 2026-08-03 | bar: w1 T2
3.7 | Course Portal Promotion (Marketing Campaigns) | 1 | 2026-08-03 | 2026-08-03 | bar: w1 T2
3.8 | Course Portal Roll-out & 3.9 Benefits Realization | 1 | 2026-08-03 | 2026-08-03 | bar: w1 T2
4 | MONITORING AND CONTROLLING | 1 | 2026-08-03 | 2026-08-03 | bar: w1 T2
5 | CLOSING | 1 | 2026-08-03 | 2026-08-03 | bar: w1 T2
Formulas:
Duration = NETWORKDAYS([Start date],[Finish Date])
Start date = MIN([Start date, row below]:D9)
Finish Date = MAX([Finish Date, row below]:E9)
Finish Date = IF([Duration]>0,WORKDAY([Start date],[Duration]-1),"")