## ChiPhi-Project
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 2 | Totals | % of Total
WBS Items
1. Project Management |  |  |  |  | 306300 | 20.13%
Project manager | 960 | 100 | 96000
Project team members | 1920 | 75 | 144000
Contractors (10% of software development and testing) |  |  | 66300
2. Hardware |  |  |  |  | 76000 | 4.996%
2.1 Handheld devices | 100 | 600 | 60000
2.2 Servers | 4 | 4000 | 16000
3. Software |  |  |  |  | 614000 | 40.36%
3.1 Licensed software | 100 | 200 | 20000
3.2 Software development* |  |  | 594000
4. Testing (10% of total hardware and software costs) |  |  | 69000 |  | 69000 | 4.536%
5. Training and Support |  |  |  |  | 202400
Trainee cost | 100 | 500 | 50000
Travel cost | 12 | 700 | 8400
Project team members | 1920 | 75 | 144000
6. Reserves (20% of total estimate) |  |  | 253540 |  | 253540 | 16.67%
Total project cost estimate |  |  |  |  | 1521240

## Estimate
1. Labor Estimate | # Units/Hrs. | Cost/Unit/Hr. | Subtotals | Calculations
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
2. Function point estimate** | Quantity | Conversion Factor | Function Points | Calculations
External inputs | 10 | 4 | 40 | 10 4
External interface fles | 3 | 7 | 21 | 3 7
External outputs | 4 | 5 | 20 | 4 5
External queries | 6 | 4 | 24 | 6 4
Logical internal tables | 7 | 10 | 70 | 7 10
Total function points |  |  | 175 | Sum above function point values
Java 2 languange equivalency value |  |  | 46 | Assumed value from reference
Source lines of code (SLOC) estimate |  |  | 8050 | 175 46
Productivity×KSLOC^Penalty (in months) |  |  | 29.2791 | 3.13 8.05^1.072 (see reference)
Total labor hours (160 hours/month) |  |  | 4684.6538 | 29.28 160
Cost/labor hour ($120/hour) |  |  | 120 | Assumed value from budget expert
Total function point estimate |  |  | 562158.459 | 4684.65 120